## Summary
Name of System - Cycle 1
Date | [6 empty] | LEGEND
Module | Passed | Resolved | Failed | Pending | UI/UX Concern | Grand Total | STATUS
EnrollEase: A Smart Web-Based Enrollment System for Imus National High School | 4 | 0 | 0 | 0 | 0 | 4 | Passed | Passed upon first check
Grand Total | 4 | 0 | 0 | 0 | 0 | 4 | Resolved | Fixed Issues
Percentage | 100% | 0% | 0% | 0% | 0% | 100% | Pending | Issues with dependency
[7 empty] | Failed | Issues that don't match the requirements or functional issue
Severity | Showstopper | Major | Minor
EnrollEase: A Smart Web-Based Enrollment System for Imus National High School | 0 | 0 | 0 |  |  |  | SEVERITY
[7 empty] | Minor | Less significant issues
[7 empty] | Major | Issues that affect a process of the system
[7 empty] | Showstopper | Issues that affect the overall of the system

## EnrollEase(Web)
ID | Module | Category | Instructions | Expected Results | Status | Actual Results | Tester | Severity | Date | Developer's Comments
1 | EnrollEase(WEB) | EnrollEase - Home Page | Steps to reproduce: 1. Enter the EnrollEase link on web browser's address bar. 2. Check to see if the homepage is displayed. | The EnrollEase home page should be displayed. | Passed |  | Fidelis, Alen N. |  | 30-Nov-2024
2 | EnrollEase(WEB) | EnrollEase - Home Page-Header - Home text | Steps to reproduce: 1. Enter the link on web browser's address bar 2.Check to see if the text "Home" is displayed. 3.Click the Home text on the header. | reload/redirecting to Hompage. | Passed |  | Lofamia, Dhaniel D. |  | 30-Nov-2024
3 | EnrollEase(WEB) | EnrollEase - Home Page-Header - About text | Steps to reproduce: 1. Enter the EnrollEase link on web browser's address bar 2. Check to see if the text "About" is displayed. 3. Click the About text on the header. | Redirecting to About page. | Passed |  | Nicol, Carlos Jr. O. |  | 30-Nov-2024
4 | EnrollEase(WEB) | EnrollEase - Home Page-Header - Account text | Steps to reproduce: 1. Enter the EnrollEase link on web browser's address bar 2. Check to see if the text "Account" is displayed. 3. Click the Account text on the header. | Show dropdown with two option, Student and Admin | Passed |  | Toledo, Marc Andrei A |  | 2024-11-30
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200